## Production
18th July 2022
Feature Tested | User Flow | Expected Result | Actual Result | Comments
Log in button | User tries to register an account | User can create an account and log in | User can create an account and log in | Works as intended
| User tries to log in with existing account | User can enter existing account details and log in | User can enter existing account details and log in | Works as intended
Navbar | User clicks home | User gets redirected to home page | User gets redirected to home page | Works as intended
| User clicks whiskeys | User gets redirected to whiskeys catalogue page | User gets redirected to whiskeys catalogue page | Works as intended
| User clicks new whiskey | User gets redirected to new whiskey page | User gets redirected to new whiskey page | Works as intended
Add whiskey | User fills out New Whiskey form | User will not be able to post as no admin role | The feature broke the page. Requires reload. | Does not work
| User fills out New Whiskey form with admin privileges | User will be able to post the form | The new whiskey has been added. | Works as intended
| User tries to add letters to "age" section of form | Error will inform them only numbers allowed. | After submission, stuck on white page. Requires reload | Does not work
Delete whiskey | User clicks delete button for whiskey | User will be able to delete whiskey | The whiskey was deleted. | Works as intended
Show whiskey | User clicks on an individual whiskey | The page is redirected and whiskey details appear | The page is redirected and whiskey details appear | Works as intended
Add whiskey tasting | User clicks "add tasting" on whiskey | The form renders | The form was renderred | Works as intended
| User submits form | submitted data renders under whiskey once submitted | Form was not renderred under the whiskey. Requires reload | Does not work
19th July 2022
Feature Tested | User Flow | Expected Result | Actual Result | Comments
Add whiskey tasting | User can use the stars to set rating | Mouse position determines number of stars | The final click of the stars determined its rating | Works as intended
| User can submit form for a tasting | Tasting form will render under the whiskey once submitted | Tasting form did not render. | Does not work
| User clicks "add tasting" | Modal will pop up to submit tastings | Modal pops up for the tasting form | Works as intended
Delete whiskey tasting | User with privileges clicks delete tasting | The tasting will be deleted | The tasting has been deleted | Works as intended
Add whiskey | User tries to add letters to 'age' section. | Once submitted, an error will pop up saying not allowed. | The page breaks once submitted. Requires reload | Does not work
| User without privileges tries to add whiskey | User should not be able to access add whiskey page. | The app breaks and requires a reload | Does not work
20th July 2022
Feature Tested | User Flow | Expected Result | Actual Result | Comments
Add whiskey tasting | User can use stars to set whiskey tasting rating | Clicking the star will set the rating | Clicking the star will set the rating | Works as intended
| User submits whiskey tasting form | The form renders after the modal is submitted. | The form renders after the modal is submitted. | Works as intended
Add whiskey | User tries to submit with letters in "age" section | Throw an error and says number only | Form is not submitted and says numbers only | Works as intended
| User without admin privilege tries to add whiskeys | User should not be able to access add whiskey page | The page breaks and goes white | Does not work
Search bar | User types whiskey in search bar | Page filters to only the whiskeys with those letters | Page filters to only the whiskeys with those letters | Works as intended
21st July 2022
Feature Tested | User Flow | Expected Result | Actual Result | Comments
Add whiskey | User without admin privilege tries to add whiskey | User should be rejected from the add whiskey page | The page breaks and goes white | Does not work
Pagination
Pagination | User goes to whiskeys page and check whiskeys | Sees only 6 whiskeys per page and page numbers | Sees only 6 whiskeys per page and page numbers | Works as intended